## Sheet1
Blister Pack Product Development Schedule
06OCT2004 Last update
Owner | Tasks | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Background
CD & HL | Contact Daniel@Bojo | bar: September 2 to September 3
CD | Contact Packaging prog dir | bar: September 2 to September 3
HL | Contact Idustrial Tech. Chair | bar: September 2 to September 3
CD | Research packaging companies | bar: September 2 to September 4
HL | Research Related Industries | bar: September 2 to September 4
CD | Research Plastic companies | bar: September 2 to September 4
HL | Research Materials and properties | bar: September 2 to September 4
CD & HL | Formulate Blister Pack process | bar: September 4 to October 4
Solid Modeling
CD & HL | Learn Solidworks | bar: September 2 to October 4
HL | Create 3D Model (SolidWorks) | bar: October 3 to December 1
Tool Prototype
CD | Machine Tooling | bar: November 3 to December 2
Experimentation
CD & HL | Devise Experiment for blister packs | bar: January 1 to January 3
CD | Run Tests | bar: January 2 to February 2
HL | Evaluate results | bar: February 1 to February 3
CD & HL | Finalize process | bar: February 3 to March 1
Modification
CD & HL | Design control scheme | bar: January 3 to March 4
CD & HL | implement controls | bar: February 2 to April 1
Testing
CD & HL | Run tests on Machine | bar: April 1 to April 4
CD & HL | Prepare for presentation | bar: April 3 to May 2
Legend:
CD = | Christian Daco
HL = | Huey Lee